## Sheet1
Key | Task | days | predecessor
A | Build Registrar UI | 2 | B
B | Design Database | 4
C | Build Advisee UI | 3 | B
D | Build Advisor UI | 3 | B
E | Build Login Functionality and Interface | 2 | B
F | Build Admin UI | 2 | B
G | Check Prerequisites functionality | 2 | B, D, G
H | Retrieve long-term plan | 2 | B, D, J
I | Evaluate Degree Completion | 4 | B, C
J | create, view, Edit Long Term Plan | 2 | B, D
K | Create, view, edit system users | 3 | B, F
L | Retrieve Schedule | 1 | B, C
M | Retrieve enrollments | 1 | B, A
N | Build Roles and Permissions | 2 | B, F
O | Advisee Search Function | 2 | B, D
P | Suggested courses per advisee | 3 | B, D, G
Q | Create, view, edit appointment | 2 | B, A, C, D, F
S | Add users to Uis | 2 | B, F, K, N